## Burndown Chart
| Estimated | 2018-05-19 | 2018-05-22 | 2018-05-25 | 2018-05-28 | 2018-05-31 | 2018-06-03 | Total hours
Proceduraly generated mazes | 5 | 5 | [5 empty] | 5
Fade in and fade our animations | 1 |  |  | 1 |  |  |  | 1
Third person view | 1 |  |  |  | 1 |  |  | 1
Memory training | 31 |  | 7 |  | 17 | 7 |  | 31
Sound effects | 1.5 | [5 empty] | 1.5 | 1.5
Menu | 1 |  |  |  | 1 |  |  | 1
Mobile and PC | 4 | [5 empty] | 0 | 0
Optimized | 3 | [5 empty] | 3 | 3
Multiple levels | 5.5 | [5 empty] | 5.5 | 5.5
Skybox | 1 |  | 1 |  |  |  |  | 1
Proccess report | 6.5 | 1 | 1 |  |  |  | 4.5 | 6.5
Project report | 21 | 0.5 | 2.5 |  | 6 | 4 | 8 | 21
Maze textures | 7 |  | 7 |  |  |  |  | 7
Statues | 3 |  | 3 |  |  |  |  | 3
Labyrinth exit | 3 |  | 3 |  |  |  |  | 3
Statue interactions | 1 |  |  | 1 |  |  |  | 1
Points | 1 | [5 empty] | 1 | 1
Actual remaining hours | 96.5 | 90 | 65.5 | 63.5 | 38.5 | 27.5 | 4
Estimated remaining hours | 96.5 | 80.4167 | 64.3333 | 48.25 | 32.1667 | 16.0833 | 0

## Project Backloog
ID | Priority | Estimated time | Story
1 | Critical | 5 | As owner I want the game to contain procedurally generated mazes
2 | Low | 1 | As owner I want the game to have smooth animation to change scenes
3 | Critical | 1 | As owner I want the game to be played from third person view
4 | Critical | 31 | As a owner I want the game to contain memory training exercise
4.1 | Critical | 7 | As owner I want the game to have pexeso minigame
4.2 | Critical | 5 | As owner I want the game to have simon says minigame
4.3 | Critical | 6 | As owner I want the game to contain route solving minigame
4.4 | Critical | 6 | As owner I want the game to contain hidden objects game
4.5 | Critical | 7 | As owner I want the game to contain quiz
5 | Medium | 1.5 | As a owner I want the game to contain sound effects
6 | Critical | 1 | As owenr I want the game to have menu
7 | Critical | 4 | As owner I want the game to run on both pc and mobile
8 | Critical | 3 | As owner I want the game to be optimized
9 | Critical | 5.5 | As owner I want multiple levels
10 | Critical | 1 | As owner I want the game to have nice skybox
11 | Critical | 6.5 | As owner I want to have proccess report
11.1 | Critical | 1 | As owner I want group policy
11.2 | Critical | 1 | As owner I want group description
11.3 | Critical | 2 | As owner I want project initiation
11.4 | Critical | 2 | As owner I want project description
11.5 | Critical | 0.5 | As owner I want project execution
12 | Critical | 21 | As owner I want project report
12.1 | Critical | 0.5 | As owner I want abstract
12.2 | Critical | 0.5 | As owner I want Introduction
12.3 | Critical | 2 | As owner I want requirements
12.4 | Critical | 6 | As owner I want analysis
12.5 | Critical | 4 | As owner I want design documentation
12.6 | Critical | 2 | As owner I want implementation documentation
12.7 | Critical | 4 | As owner I want test documentation
12.8 | Critical | 1 | As owner I want conclusion and results
12.9 | Critical | 1 | As owner I want project future
13 | High | 7 | As owner I want the maze to look nice
14 | High | 3 | As owner I want the maze to contain statues
15 | Medium | 3 | As owner I want I want nice labyrinth exit in the center
16 | Critical | 1 | As owner I want minigames to be accesed by statues
17 | Critical | 1 | As owner I want the level to end when certain amount of point has been collected

## 19.05
PB-ID | ID | Task title | Responsible | Estimated | Status
1 | 1 | Find algorythm for maze genration | Marek | 2 | Done
1 | 2 | Implement algorythm in project | Marek | 3 | Done
1 | 3 | Test maze generation | Marek | 1 | Done
11.1 | 4 | Group contract | Kajul | 1 | Done
12.1 | 5 | Abstract | Kajul | 0.5 | Done

## 22.05
PB-ID | ID | Task title | Responsible | Estimated | Status
14 | 1 | Find nice bush textures | Marek | 4 | Done
14 | 2 | Find nice pavement textures | Marek | 3 | Done
12.3 | 3 | Write requirements | Kajul | 2 | Done
12.2 | 4 | Write introduction | Kajul | 0.5 | Done
15 | 5 | Find statues on asset store | Marek | 2 | Done
15 | 6 | Import statues into scenes | Marek | 1 | Done
10 | 7 | Find nice skybox | Marek | 1 | Done
15 | 8 | Find nice assets for labyrinth exit | Marek | 1 | Done
15 | 9 | Design nice looking exit with lights and particles | Marek | 2 | Done
4.1 | 10 | Find card assets | Kajul | 1 | Done
4.1 | 11 | Implement pexeso scripts | Kajul | 3 | Done
4.1 | 12 | Implement gameplay scripts | Kajul | 2 | Done
4.1 | 13 | Test pexeso minigame | Kajul | 1 | Done
11.2 | 144 | Write group description | Kajul | 1 | Done

## 25.05
PB-ID | ID | Task title | Responsible | Estimated | Status
2 | 1 | Make fade in and fade out transition animations | Marek | 1 | Done
18 | 2 | Implement statue interactions | Marek | 1 | Done

## 28.05
PB-ID | ID | Task title | Responsible | Estimated | Status
4.2 | 1 | Find simon says game online | Marek | 1 | Done
4.2 | 2 | Implement minigame | Marek | 1 | Done
4.2 | 3 | Create associations with statue and test | Marek | 2 | Done
4.3 | 4 | Come up with minigame idea | Marek | 1 | Done
4.3 | 5 | Find map for the minigame | Marek | 0.5 | Done
4.3 | 6 | Come up with stories containing route | Marek | 1 | Done
4.3 | 7 | Implement grid layout on the map | Marek | 1 | Done
4.3 | 8 | Implement game mechanichs | Marek | 1.5 | Done
4.3 | 9 | Test minigame | Marek | 1 | Done
3 | 10 | Import and implement third person controlls | Kajul | 1 | Done
6 |  | Implement menu | Kajul | 1 | Done
4.4 | 11 | Create scene containing the room image | Kajul | 1 | Done
4.4 | 12 | Implement game mechanics responsible for hiding objects | Kajul | 4 | Done
4.4 | 13 | Implement firescore after game is won | Kajul | 1 | Done
12.4 | 14 | Create Usecase diagram | Kajul | 2 | Done
12.4 | 15 | Write Usecase descriptions | Kajul | 2 | Done
12.4 | 16 | Create Domain model | Marek | 2 | Done

## 31.05
PB-ID | ID | Task title | Responsible | Estimated | Status
12.2 | 1 | Edit introduction | Kajul | 0.5 | Done
12.4 | 2 | Edit use case documents | Marek | 0.5 | Done
4.5 | 3 | Find questions for quiz | Kajul | 2 | Done
4.5 | 4 | Implement scene showing the questions | Kajul | 2 | Done
4.5 | 5 | Implement mechanics for the quiz | Kajul | 2 | Done
4.5 | 6 | Test the quiz minigame | Kajul | 1 | Done
12.5 | 7 | Create activity diagram and decsription | Marek | 1 | Done
12.5 | 8 | Create sequence diagram and description | Marek | 1 | Done
12.5 | 9 | Create class diagram with desacription | Marek | 2 | Done

## 03.06
PB-ID | ID | Task title | Responsible | Estimated | Status
11.5 | 1 | Merge scrum documetation with main document | Marek | 0.5 | Done
5 | 2 | Find some sound clip for the fire | Marek | 1 | Done
5 | 3 | Implement temple sound effect in game | Marek | 0.5 | Done
8 | 4 | Go through the files in project and check sorting in folders | Kajul | 1 | Done
8 | 5 | Check if scripts follow SOLID | Kajul | 1 | Done
8 | 6 | Delete unneccessary files | Marek | 1 | Done
9 | 7 | Implement second level | Kajul | 2 | Done
9 | 8 | Redo scripts responsible for loading previous level | Marek | 1 | Done
9 | 9 | Implement select level in menu | Marek | 0.5 | Done
9 | 10 | Create new content for quiz and room minigame | Kajul | 2 | Done
12.6 | 11 | Create screenshots of code for documentation snippets | Marek | 1 | Done
12.6 | 12 | Write implementation document using snippets and description | Marek | 1 | Done
17 | 13 | Write script responsible for switching level when enough fire point is collected | Marek | 1 | Done
11.3 | 14 | Write the initiation for the process report | Marek | 2 | Done
11.4 | 15 | Write the project decription in process report | Kajul | 2 | Done
12.7 | 16 | Perform a requirement testing | Kajul | 3 | Done
12.7 | 17 | Write testing documetation | Kajul | 1 | Donne
12.8 | 18 | Write result and conclusion | Marek | 1 | Done
12.9 | 19 | Write project future | Marek | 1 | Done