## Burndown Chart
| Estimated | 2018-05-19 | 2018-05-22 | 2018-05-25 | 2018-05-28 | 2018-05-31 | 2018-06-03 | Total hours
Proceduraly generated mazes | 5 | 5 | [5 empty] | 5
Fade in and fade our animations | 1 | [6 empty] | 0
First person view | 8 | [6 empty] | 0
Memory training | 5 |  | 6 |  |  |  |  | 6
Sound effects | 6 | [6 empty] | 0
Menu | 2 | [6 empty] | 0
Mobile and PC | 2 | [6 empty] | 0
Optimized | 8 | [6 empty] | 0
Multiple levels | 20 | [6 empty] | 0
Skybox | 1 |  | 1 |  |  |  |  | 1
Proccess report | 11 | 1 | [5 empty] | 1
Project report | 30 | 0.5 | 2.5 |  |  |  |  | 3
Mobile controlls | 10 | [6 empty] | 0
Maze textures | 7 |  | 7 |  |  |  |  | 7
Statues | 3 |  | 3 |  |  |  |  | 3
Background music | 2 | [6 empty] | 0
Labyrinth exit | 3 |  | 3 |  |  |  |  | 3
| 0 | [6 empty] | 0
| 0 | [6 empty] | 0
Actual remaining hours | 124 | 117.5 | 108 | 108 | 108 | 108 | 108
Estimated remaining hours | 124 | 106.2857 | 88.5714 | 70.8571 | 53.1429 | 35.4286 | 17.7143

## Project Backloog
ID | Priority | Estimated time | Story
1 | Critical | 5 | As owner I want the game to contain proceduraly generated mazes
2 | Low | 1 | As owenr I want the game to have smooth animation to change scenes
3 | Critical | 8 | As owner I want the game to be played from first person view
4 | Critical | 5 | As a owner I want the game to contain memory training exercise
4.1 | Critical | 5 | As owner I want the goma to have pexeso minigame
5 | Medium | 6 | As a owner I want the game to contain sound effects
6 | Critical | 2 | As owenr I want the game to have menu
7 | Critical | 2 | As owner I want the game to run on both pc and mobile
8 | Critical | 8 | As owner I want the game to be optimized
9 | Critical | 20 | As owner I want multiple levels
10 | Critical | 1 | As owner I want the game to have nice skybox
11 | Critical | 11 | As owner I want to have proccess report
11.1 | Critical | 1 | As owner I want group policy
11.2 | Critical | 1 | As owner I want group description
11.3 | Critical | 2 | As owner I want project initiation
11.4 | Critical | 2 | As owner I want project description
11.5 | Critical | 5 | As owner I want project execution
12 | Critical | 30 | As owner I want project report
12.1 | Critical | 0.5 | As owner I want abstract
12.2 | Critical | 0.5 | As owner I want Introduction
12.3 | Critical | 2 | As owner I want requirements
12.4 | Critical | 8 | As owner I want analysis
12.5 | Critical | 8 | As owner I want design documentation
12.6 | Critical | 5 | As owner I want implementation documentation
12.7 | Critical | 3 | As owner I want test documentation
12.8 | Critical | 2 | As owner I want conclusion and results
12.9 | Critical | 1 | As owner I want project future
13 | Critical | 10 | As owner I want the game to be controlled via on screen buttons on mobile devices
14 | High | 7 | As owner I want the maze to look nice
15 | High | 3 | As owner I want the maze to contain statues, which will lead to mini games
16 | Medium | 2 | As owner I want nice background music
17 | Medium | 3 | As owner I want I want nice labyrinth exit in the center
18
19
20
21
22
23
24
25
26
27
28
29
30

## 19.04
PB-ID | ID | Task title | Responsible | Estimated | Status
1 | 1 | Find algorythm for maze genration | Marek | 2 | Done
1 | 2 | Implement algorythm in project | Marek | 3 | Done
1 | 3 | Test maze generation | Marek | 1 | Done
11.1 | 4 | Group contract | Kajul | 1 | Done
12.1 | 5 | Abstract | Kajul | 0.5 | Done

## 22.04
PB-ID | ID | Task title | Responsible | Estimated | Status
14 | 1 | Find nice bush textures | Marek | 4 | Done
14 | 2 | Find nice pavement textures | Marek | 3 | Done
12.3 | 3 | Write requirements | Kajul | 2 | Done
12.2 | 4 | Write introduction | Kajul | 0.5 | Done
15 | 5 | Find statues on asset store | Marek | 2 | Done
15 | 6 | Import statues into scenes | Marek | 1 | Done
10 | 7 | Find nice skybox | Marek | 1 | Done
17 | 8 | Find nice assets for labyrinth exit | Marek | 1 | Done
17 | 9 | Design nice looking exit with lights and particles | Marek | 2 | Done
4.1 | 10 | Find card assets | Kajul | 1 | Done
4.1 | 11 | Implement pexeso scripts | Kajul | 3 | Done
4.1 | 12 | Implement gameplay scripts | Kajul | 2 | Done
4.1 | 13 | Test pexeso minigame | Kajul | 1 | Done

## 25.04
PB-ID | ID | Task title | Responsible | Estimated | Status

## 28.04
PB-ID | ID | Task title | Responsible | Estimated | Status

## 01.05
PB-ID | ID | Task title | Responsible | Estimated | Status

## 03.05
PB-ID | ID | Task title | Responsible | Estimated | Status