## Burndown Chart
| Estimated | 2018-05-19 | 2018-05-22 | 2018-05-25 | 2018-05-28 | 2018-05-31 | 2018-06-03 | Total hours
Proceduraly generated mazes | 4 | 4 | [5 empty] | 4
Fade in and fade our animations | 1 | [6 empty] | 0
First person view | 8 | [6 empty] | 0
Memory training | 30 | [6 empty] | 0
Sound effects | 5 | [6 empty] | 0
Menu | 2 | [6 empty] | 0
Mobile and PC | 2 | [6 empty] | 0
Optimized | 8 | [6 empty] | 0
Multiple levels | 20 | [6 empty] | 0
Skybox | 2 | [6 empty] | 0
Proccess report | 4 | 1 | [5 empty] | 1
Project report | 1 | [6 empty] | 0
Mobile controlls | 10 | [6 empty] | 0
Actual remaining hours | 97 | 92 | 92 | 92 | 92 | 92 | 92
Estimated remaining hours | 97 | 83.1429 | 69.2857 | 55.4286 | 41.5714 | 27.7143 | 13.8571

## Project Backloog
ID | Priority | Estimated time | Story
1 | Critical | 4 | As owner I want the game to contain proceduraly generated mazes
2 | Low | 1 | As owenr I want the game to have smooth animation to change scenes
3 | Critical | 8 | As owner I want the game to be played from first person view
4 | Critical | 30 | As a owner I want the game to contain memory training exercise
5 | Critical | 5 | As a owner I want the game to coontain sound effects
6 | Critical | 2 | As owenr I want the game to have menu
7 | Critical | 2 | As owner I want the game to run on both pc and mobile
8 | Critical | 8 | As owner I want the game to be optimized
9 | Critical | 20 | As owner I want multiple levels
10 | Critical | 2 | As owner I want the game to have nice skybox
11 | Critical | 4 | As owner I want to have proccess report
11.1 | Critical | 1 | As owner I want requirements
11.2 | Critical | 1 | As owner I want group contract
11.3 | Critical | 2 | As owner I want personal reflections
12 | Critical | 1 | As owner I want project report
13 | Critical | 10 | As owner I want the game to be controlled via on screen buttons on mobile devices
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## 19.04
PB-ID | ID | Task title | Responsible | Estimated | Status
1 | 1 | Create algorithm for maze generation | Marek | 3 | Done
1 | 2 | Implement creating walls and floors | Marek | 1 | Done
1 | 3 | Finish maze generation | Marek | 1 | Done
11.2 | 4 | Group contract | Kajul | 1 | Done

## 24.04
PB-ID | ID | Task title | Responsible | Estimated | Status

## 26.04
PB-ID | ID | Task title | Responsible | Estimated | Status

## 28.04
PB-ID | ID | Task title | Responsible | Estimated | Status

## 01.05
PB-ID | ID | Task title | Responsible | Estimated | Status

## 03.05
PB-ID | ID | Task title | Responsible | Estimated | Status