## Burndown Chart
| Estimated | 2018-05-19 | 2018-05-22 | 2018-05-25 | 2018-05-28 | 2018-05-31 | 2018-06-03 | Total hours
Proceduraly generated mazes | 5 | 5 | [5 empty] | 5
Fade in and fade our animations | 1 | [6 empty] | 0
First person view | 3 | [6 empty] | 0
0
0
0
0
0
0
0
0
0
0
Actual remaining hours | 9 | 4 | 4 | 4 | 4 | 4 | 4
Estimated remaining hours | 9 | 7.7143 | 6.4286 | 5.1429 | 3.8571 | 2.5714 | 1.2857

## Project Backloog
ID | Priority | Estimated time | Story
1 | Critical | 5 | As deevelopers we want game to contain proceduraly generated mazes
2 | Low | 1 | Game should have smooth animation to change scenes
3 | Critical | 3 | Users character should see game from first person view

## 19.04
PB-ID | ID | Task title | Responsible | Estimated | Status
1 | 1 | Create algorithm for maze generation | Marek | 3 | Done
1 | 2 | Implement creating walls and floors | Marek | 1 | Done
1 | 3 | Finish maze generation | Marek | 1 | Done

## 24.04
PB-ID | ID | Task title | Responsible | Estimated | Status

## 26.04
PB-ID | ID | Task title | Responsible | Estimated | Status

## 28.04
PB-ID | ID | Task title | Responsible | Estimated | Status

## 01.05
PB-ID | ID | Task title | Responsible | Estimated | Status

## 03.05
PB-ID | ID | Task title | Responsible | Estimated | Status